EXPENSIFY

Project Plan, Architecture & Development Roadmap

AI-powered personal expense tracker — Version 1.0  |  March 2026

Document Overview

This document captures the complete planning, architecture, and development roadmap for Expensify — a smart expense tracking mobile application. It covers the product vision, full system architecture, 4-stage roadmap, and a detailed sprint-by-sprint breakdown for Stage 1.

| Project | Expensify — AI Expense Tracker |
| --- | --- |
| Platform | React Native (iOS + Android) |
| Backend | Supabase (Postgres + Auth + Realtime + Storage) |
| AI Services | Anthropic Claude API + OpenAI Whisper |
| Stage 1 Timeline | 6–8 weeks (7 sprints) |
| Stage 1 Target Users | 5–10 demo users |
| Long-term Goal | 1,000+ users, public App Store launch |
| Document Date | March 2026 |

# 1. Product Vision & Feature Set

Expensify is an AI-powered personal finance app that makes expense tracking effortless. The core insight: most people abandon expense apps because logging is too slow and insights are not actionable. Expensify solves this with voice-first input, automatic categorization, and smart insights that tell you something useful.

## 1.1  Input methods

- Manual add — amount, category, merchant, date, optional note

- Voice / speech-to-text — tap mic, speak naturally ("Spent 480 on pizza"), saved in under 2 seconds

- Bill scan — photograph a receipt; Claude Vision extracts merchant, total, date, and line items automatically

- Ultra-fast mode — app opens directly to mic; no navigation required

## 1.2  Categorization

- AI auto-categorization via Claude API on every expense

- 12 default categories: Food, Transport, Shopping, Health, Entertainment, Home, Education, Bills, Personal, Travel, Fitness, Other

- Manual override — user can correct wrong categories; corrections improve future suggestions

- Tags support — free-form tagging in addition to categories

## 1.3  Dashboard & visualization

- Stat cards: today / this week / this month totals

- Pie chart: spending by category for selected period

- Bar chart: daily spend over past 7 days

- Custom date range filter

- Recent expenses quick-list (last 5)

## 1.4  Budget management

- Monthly budget setting with remaining balance tracker

- Per-category budget limits

- Color-coded progress bar: green → amber at 80% → red at 100%

- In-app alert when crossing thresholds

## 1.5  AI-powered insights (Stage 2+)

- Nightly generated insights: "You spent 30% more on food this week"

- AI assistant: answer natural language spending questions

- Savings recommendations based on spending patterns

## 1.6  Advanced features (Stage 2–4)

- Recurring expenses — auto-add monthly rent, subscriptions

- Family groups — shared expense tracking with real-time sync

- Push notifications — daily reminders and budget alerts

- Export to CSV and PDF

- Home-screen widget (iOS and Android)

- Bank statement import (UPI / bank CSV)

- WhatsApp bot integration

# 2. System Architecture

Expensify uses a mobile-first architecture built on Supabase as the unified backend platform, with AI services integrated via Anthropic Claude and OpenAI Whisper APIs.

## 2.1  Architecture layers

| Layer | Technology | Purpose |
| --- | --- | --- |
| Client app | React Native + Expo Router | iOS and Android from a single codebase |
| State management | Zustand + React Query | Local state and server data synchronization |
| API gateway | Supabase Edge Functions (Deno/TS) | Auth middleware, rate limiting, request routing |
| Core services | Supabase Edge Functions | Expense, budget, family, export logic |
| AI services | Claude API + Whisper API | Categorization, voice parsing, insights, OCR |
| Database | Supabase Postgres + RLS | All persistent data with row-level security |
| Realtime | Supabase Realtime (WebSocket) | Family group live sync |
| File storage | Supabase Storage | Bill and receipt images |
| Cache | Redis via Upstash (Stage 4) | Session cache, aggregation cache |
| Auth | Supabase Auth | Email, Google OAuth, Apple Sign-in |
| Background jobs | pg_cron | Recurring expenses, nightly insights, budget alerts |
| Push notifications | Expo Push + FCM/APNs | Device notifications |

## 2.2  Key architecture decisions

- Supabase as unified backend: Provides Postgres, Auth, Realtime, Storage, and Edge Functions in one platform. Eliminates stitching multiple services for a small team.

- Row-level security from Day 1: All tables enforce RLS at Postgres level so users can only access their own data. Family group data governed by role-based policies. Must be set up in Sprint 0.

- Amounts stored as integers (paise): All monetary values stored as smallest currency unit. Never store floats. Display layer converts. Prevents float precision bugs forever.

- Claude Haiku for speed-critical paths: Voice parsing and auto-categorization use claude-haiku-4-5 for sub-600ms responses. Bill scanning and the AI assistant use claude-sonnet-4-6.

- Cached AI insights: Nightly pg_cron job generates insights and stores them. Dashboard reads from cache — no AI call on page load.

- Client-side dashboard stats: Totals, breakdowns, and charts computed on client from React Query cache using useMemo. No extra DB calls.

- Schema designed for Stage 2+ from Day 1: Tables include columns like group_id, source, bill_image_url that won't be used until later. Adding on Day 1 is free. Adding to production schema later is painful.

## 2.3  Database schema (v1)

All tables must be created in Sprint 0 with RLS enabled before any data is written.

| Table | Primary columns | Future-ready columns |
| --- | --- | --- |
| users | id uuid PK, email, name, avatar_url | currency, timezone, monthly_budget bigint, notification_prefs jsonb |
| expenses | id uuid PK, user_id FK, amount bigint, category, merchant, description, expense_date, created_at | group_id uuid, source text, bill_image_url text, tags text[] |
| budgets | id uuid PK, user_id FK, month text (YYYY-MM), total_budget bigint | category_budgets jsonb, alert_at_pct int, alerted_80 bool, alerted_100 bool |
| categories | id, name, icon, color | Static seed data — all 12 categories seeded on Day 1 |
| recurring_expenses | id, user_id FK, amount, merchant, category | frequency RRULE, next_due_date, is_active bool — Stage 3 |
| family_groups | id, owner_id FK, name, invite_code | members jsonb array — Stage 3 |
| insights | id, user_id FK, type, content text, generated_at | group_id, data_snapshot jsonb, is_read bool — Stage 2 |

## 2.4  AI service flows

### Voice-to-expense (target: under 2 seconds)

- User taps mic; app opens directly to voice capture (Expo AV)

- Audio streamed to Whisper API; transcript returned in ~600ms

- Transcript sent to claude-haiku-4-5 with structured extraction prompt

- Claude returns JSON: { amount, merchant, category, date, description }

- Expense inserted to DB; confirmation shown with one-tap correction option

### Bill scan flow

- User photographs receipt; image compressed to ~500KB client-side

- JPEG uploaded to Supabase Storage private bucket

- Signed URL sent to claude-sonnet-4-6 with extraction prompt

- Claude Vision returns merchant, total, date, and itemized list

- User confirms extracted data before saving

### AI cost estimates at 50 users

| Feature | Model | Est. cost per use | Monthly total |
| --- | --- | --- | --- |
| Voice parsing | claude-haiku-4-5 + Whisper | ~₹0.08 | ~₹200–400 |
| Bill scan | claude-sonnet-4-6 Vision | ~₹0.80–2.40 | ~₹400–800 |
| Nightly insights | claude-haiku-4-5 batch | ~₹0.16/user/day | ~₹240 |
| AI assistant | claude-sonnet-4-6 | ~₹0.40/query | Variable |
| Total |  |  | ~₹800–2,000/month |

# 3. Four-Stage Development Roadmap

The project is divided into four stages, each building on the previous. Stage 1 targets demo-readiness. Stage 2 adds AI differentiators. Stage 3 drives retention. Stage 4 prepares for scale.

| Stage 1 6–8 weeks | Foundation — Core app, demo ready Working expense CRUD, dashboard with charts, budget tracking. No AI. Built for 5–10 users. |
| --- | --- |

| Stage 2 5–6 weeks | Intelligence — The wow factor Voice input, bill scanning, AI auto-categorization, smart insights. The differentiator. |
| --- | --- |

| Stage 3 5–7 weeks | Social + Scale — Retention engine Family groups, recurring expenses, push notifications, export. Turns one user into five. |
| --- | --- |

| Stage 4 Ongoing | Production — Ready for thousands Infrastructure hardening, monetization, analytics, growth loops. Public App Store launch. |
| --- | --- |

## 3.1  Stage 1 — Foundation

### Features to build

- Email + Google OAuth login

- Manual expense add: amount, category, merchant, date, note

- Expense list with search and category filter

- Dashboard: today / week / month stat cards

- Pie chart (category breakdown) and bar chart (daily spend)

- Monthly budget: set, track, warning at 80%

- Custom date range filter

- Edit and delete expense

- Basic profile and currency settings

### Stage 1 tech stack

| Package | Purpose |
| --- | --- |
| react-native + expo ~50 | Core framework and build tooling |
| expo-router 3.x | File-based navigation |
| @supabase/supabase-js 2.x | Backend client |
| zustand 4.x | Local state management |
| @tanstack/react-query 5.x | Server state and caching |
| nativewind 4.x | Tailwind CSS for React Native |
| victory-native | Charts (pie, bar) |
| typescript 5.x | Type safety throughout |

## 3.2  Stage 2 — Intelligence

- Ultra-fast voice mode: one tap, speak, saved under 2 seconds

- Whisper STT + Claude parsing for amount, category, merchant

- AI auto-categorization on manual add

- Receipt photo scan via Claude Vision

- Smart insight cards on dashboard (nightly generated)

- Basic AI assistant for natural language spending questions

- Per-category budget limits

## 3.3  Stage 3 — Social + Scale

- Family groups: create, invite via link or code

- Shared expense view and combined family dashboard

- Role-based access: owner / member / viewer

- Real-time sync via Supabase Realtime

- Recurring expense auto-add engine (pg_cron)

- Push notifications: daily reminders and budget alerts

- Export to CSV and PDF

## 3.4  Stage 4 — Production

### Monetization tiers

| Tier | Price | Includes |
| --- | --- | --- |
| Free | ₹0 / month | Manual add only, 3-month history, 1 budget |
| Pro | ₹199 / month | Voice, bill scan, AI insights, unlimited history, export |
| Family | ₹399 / month | Everything in Pro + family group up to 6 members |

### Infrastructure upgrades

- Supabase Pro plan (dedicated DB, higher connection limits)

- Redis caching for aggregations (Upstash)

- CDN for bill images (Cloudflare)

- Error tracking (Sentry) and analytics (PostHog)

- Rate limiting and per-user AI cost caps

### Growth features

- Referral system: invite a friend, both get 1 month Pro free

- iOS and Android home-screen widgets

- Bank statement import: UPI and bank CSV parsing

- WhatsApp bot: add expense via WhatsApp message

# 4. Stage 1 — Detailed Sprint Plan

Stage 1 is 7 sprints across 6–8 weeks. Each sprint has a clear goal, ordered task list, and a done-when checklist. Do not start the next sprint until the current checklist is complete.

| Sprint | Name | Days | End goal |
| --- | --- | --- | --- |
| 0 | Project setup & infrastructure | 1–3 | Running app on device, Supabase connected, full schema deployed |
| 1 | Authentication & user profile | 4–7 | Sign up, Google login, session persistence, protected routes |
| 2 | Expense CRUD | 8–13 | Add, list, edit, delete with categories and search |
| 3 | Dashboard, charts & filters | 14–20 | Stat cards, pie chart, bar chart, date range filter |
| 4 | Budget tracking | 21–26 | Monthly budget, progress bar, 80%/100% warnings |
| 5 | Polish & UX | 27–33 | Loading states, empty states, dark mode, haptics |
| 6 | Testing & demo release | 34–42 | Bug fixes, TestFlight build, demo video, 5–10 beta users |

| Sprint 0 Days 1–3 | Project setup & infrastructure Complete foundation: running app on device, Supabase connected, full DB schema, RLS enabled. |
| --- | --- |

### Tasks

- Create Expo project with TypeScript template: npx create-expo-app Expensify --template

- Configure Expo Router for file-based navigation

- Create Supabase project (free tier at supabase.com)

- Install Supabase JS client and all dependencies

- Create .env file with SUPABASE_URL and SUPABASE_ANON_KEY (never hardcode keys)

- Run complete DB schema SQL in Supabase SQL editor — all tables at once

- Enable Row Level Security on ALL tables immediately

- Install Zustand, React Query, NativeWind, Victory Native

- Create folder structure: app/, components/, hooks/, lib/, store/, types/, constants/

- Initialize Git repo and make initial commit

- Run on physical device via Expo Go — confirm it launches

Critical: Run Complete Schema on Day 1

Include ALL columns even those not used until Stage 2 or 3:

expenses: group_id, source, bill_image_url, tags

budgets: category_budgets jsonb, alert_at_pct, alerted_80, alerted_100

users: currency, timezone, notification_prefs jsonb

Changing a production schema later is painful. Add nullable columns now. It costs nothing.

| Sprint 1 Days 4–7 | Authentication & user profile Email + Google OAuth working. Session persists. Protected route guard in place. |
| --- | --- |

### Tasks

- Enable Email + Google OAuth in Supabase Authentication settings

- Build login screen: email/password fields + Google Sign-in button

- Build sign-up screen with client-side validation

- Set up auth state listener in Zustand authStore

- Implement protected route logic in app/_layout.tsx

- On first sign-up: insert row into users table with id = auth.uid()

- Build profile screen: display name, currency picker

- Implement logout: supabase.auth.signOut() + clear Zustand

- Write RLS policy: SELECT/UPDATE on users WHERE id = auth.uid()

- Test: kill app, reopen — confirm still logged in

- Test: attempt direct navigation while logged out — confirm redirect

Security: RLS Must Be Set Before Any Data

CREATE POLICY users_rls ON users USING (id = auth.uid());

Without this, any authenticated user can read any other user's data.

Test all RLS policies using Supabase's built-in policy tester before writing real data.

### Done when

- New user can sign up and reach home screen

- Google OAuth works on a real device

- Session persists across app restarts

- Unauthenticated navigation is blocked

| Sprint 2 Days 8–13 | Expense CRUD — add, list, edit, delete The core loop. Every other screen depends on this working correctly. |
| --- | --- |

### Tasks

- Build Add Expense screen with numeric amount input

- Build CategoryPicker: 12-category grid with icons

- Add date picker (default today)

- Add optional description field

- Wire save: insert to Supabase expenses table

- Write RLS: CRUD on expenses WHERE user_id = auth.uid()

- Build expenses list screen (FlatList)

- Create ExpenseRow: icon, merchant, amount, date

- Tap to edit: navigate to edit screen with prefilled data

- Swipe-to-delete with confirmation dialog

- Search bar: filter by merchant/description

- Category filter tabs at top of list

- useExpenses hook with React Query (fetch, mutate, invalidate)

- Optimistic UI on add: item appears instantly

Rule: Store Amounts as Integers (Paise)

NEVER store monetary values as floats.

₹480.50 is stored as 48050 (integer, paise). $12.99 is stored as 1299 (cents).

DB column type: bigint. Display: amount / 100 formatted with Intl.NumberFormat.

This rule applies to ALL monetary columns. No exceptions ever.

### Done when

- Add expense → appears instantly in list (optimistic UI)

- Edit amount, category, date, note — all work

- Delete removes the row immediately

- Search and category filter both work

- Data survives app restart

| Sprint 3 Days 14–20 | Dashboard, charts & date filters The demo screen. Stat cards, pie chart, bar chart, date range filter. |
| --- | --- |

### Tasks

- Install Victory Native

- Build useDashboardStats hook — compute from React Query cache using useMemo

- Build StatCard component: label, large number, period

- Add Today / Week / Month filter tabs

- Build PieChart: category breakdown for selected period

- Build BarChart: daily spend for past 7 days

- Category breakdown list: icon, name, percentage, amount

- Recent expenses mini-list (last 5)

- DateRangePicker component: from/to date selection

- Greeting with user name and today's date

- Empty state for no-expense scenario

- Pull-to-refresh

Performance: Compute Stats Client-Side

Do NOT make separate DB queries for dashboard totals.

Expenses are already in React Query's cache from the expenses screen.

useDashboardStats derives all numbers from that cache with useMemo.

Result: dashboard renders instantly and works offline with zero extra DB calls.

### Done when

- Stat cards show correct totals for each period

- Charts render correct data for selected period

- Date range filter updates all charts

- Dashboard looks polished enough for a demo screenshot

| Sprint 4 Days 21–26 | Budget tracking Set monthly budget, track remaining balance, warn at 80% and 100%. |
| --- | --- |

### Tasks

- Budget settings screen: number input for monthly total

- Optional per-category budget limits

- RLS policy on budgets table

- useBudget hook: fetch current month's budget

- BudgetCard on dashboard: spent / total display

- BudgetProgressBar: green → amber → red

- Remaining balance in human-readable format

- In-app alert banner at 80% threshold

- Handle no-budget state with CTA

- Handle new month: no row = fresh start

Budget Month Format

Store as text: '2026-03' (YYYY-MM format).

Query: WHERE month = to_char(now(), 'YYYY-MM')

New month = no row = show 'Set your budget' prompt.

This gives automatic monthly reset with no cron job needed.

### Done when

- User can set and update monthly budget

- Progress bar reflects correct spend vs budget

- Color changes at 80% and 100%

- New month starts fresh

| Sprint 5 Days 27–33 | Polish, UX & error handling The gap between 'it works' and 'it feels professional'. Non-negotiable. |
| --- | --- |

### Tasks

- Skeleton loaders on every screen that fetches data

- Empty states with illustration and CTA on all screens

- Error states with retry button for network failures

- Toast notifications for all mutation success/error

- Haptic feedback on add and delete (expo-haptics)

- Keyboard-aware scroll on add expense screen

- Full dark mode using NativeWind dark: prefix

- Polish tab bar: icons, colors, active states

- Standardize spacing, font sizes, color tokens

- Form validation messages

- Confirm dialog before delete

- Offline banner when no internet

- App icon and splash screen design

### Done when

- No blank white flashes on any screen

- Every list has an empty state

- Every action has visible feedback

- Dark mode works throughout

- A stranger can use the app without guidance

| Sprint 6 Days 34–42 | Testing, demo prep & Stage 1 release Harden for real users. TestFlight build, demo video, 5–10 beta users. |
| --- | --- |

### Tasks

- Full end-to-end test: sign up → add 10 expenses → verify dashboard totals

- Test on both iOS and Android physical devices

- Test offline behavior in airplane mode

- Test edge cases: zero budget, no expenses, very large amounts

- Fix all critical bugs

- Build iOS via EAS Build → submit to TestFlight

- Build Android APK via EAS Build → share direct link

- Record 60-second screen recording demo

- Send to 5–10 beta users with simple instructions

- Create feedback form (5 questions, Google Form)

- After 1 week: review feedback, decide Stage 2 priorities

### Feedback questions for beta users

- Did you add at least one expense in your first session?

- Did you return to the app after day 1?

- What category did you use most?

- What confused or frustrated you?

- What do you wish the app could do that it cannot yet?

Stage 1 Complete When:

✓ App runs on iOS and Android without crashes

✓ 5–10 real users have installed and actively used it

✓ Demo video is recorded and shareable

✓ Feedback collected and reviewed

✓ Stage 2 priorities decided based on real feedback

✓ You can demo the full flow in under 2 minutes

# 5. Guiding Principles

## Build for extension, not perfection

Every table, route, and component should be designed so Stage 2 and 3 features plug in without a rewrite. RLS policies, typed enums, nullable columns for future use, separate expense_date and created_at fields — these cost nothing on Day 1 and save weeks of migration work later.

## Validate before you build

Do not start Stage 3 until real users have used Stage 2 for at least two weeks. The feature you assume they want is rarely the one they actually need. Ship, observe real behavior, collect structured feedback, then build. Assumptions built on assumptions create products nobody uses.

## Control AI costs from Day 1

Always cache AI outputs. Never call Claude on a page load. Set per-user daily call limits before any AI feature goes live. At 50 users with uncapped AI calls, costs can easily exceed ₹10,000/month. Design frugality early: batch nightly, serve from cache, gate AI features behind the Pro tier in Stage 4.

# 6. Risks & Mitigations

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Schema migration pain in production | High | Run complete schema Day 1; Stage 1 has no live users |
| AI costs exceed budget | High | Cache nightly, cap per-user calls, gate AI behind Pro tier |
| RLS misconfiguration leaks data | Critical | Test all policies before any data written; use Supabase policy tester |
| Float precision bugs in money | High | Store as paise integers — enforce in code review, no exceptions |
| React Native perf on older Android | Medium | Use FlatList with keyExtractor; avoid inline styles in lists |
| Low beta user engagement | Medium | Pick motivated users, provide onboarding, follow up on day 3 |
| App Store / Play Store rejection | Medium | Follow guidelines; avoid financial advice claims in copy |
| Supabase free tier limits | Low (Stage 1) | Free tier: 500MB DB, 2GB storage — plenty for Stage 1 |

# 7. Quick Reference

## Key install commands

# Create project npx create-expo-app Expensify --template  # Core dependencies npx expo install @supabase/supabase-js expo-router npx expo install nativewind zustand @tanstack/react-query npx expo install victory-native npx expo install expo-av expo-camera expo-haptics expo-notifications  # Build for testing npx eas build --platform ios --profile preview npx eas build --platform android --profile preview

## Essential RLS policies

-- Users table CREATE POLICY users_rls ON users   USING (id = auth.uid());  -- Expenses table   CREATE POLICY expenses_rls ON expenses   USING (user_id = auth.uid());  -- Budgets table CREATE POLICY budgets_rls ON budgets   USING (user_id = auth.uid());  -- Run this to verify RLS is enabled SELECT tablename, rowsecurity FROM pg_tables   WHERE schemaname = 'public';

## Amount formatting utility

// Always store as integer (paise/cents) // NEVER store as float  export const formatAmount = (   paise: number,   currency: string = 'INR' ): string => {   return new Intl.NumberFormat('en-IN', {     style: 'currency',     currency,     minimumFractionDigits: 0,     maximumFractionDigits: 0,   }).format(Math.round(paise) / 100); };  // Usage: formatAmount(48050) => '₹480'

Expensify Project Plan v1.0  |  March 2026  |  Refer to this document at the start of each sprint.